Bansilal Ramnath Agarwal Charitable Trust’s

VISHWAKARMA INSTITUTE OF TECHNOLOGY – PUNE

CS2311:		Software Engineering

| Division |  |  | SY CS-A |
| --- | --- | --- | --- |
| Batch |  |  | 3 |
| GR Number (PRN) |  |  | 12413610 |
| Roll No. |  |  | 10 |
| Name |  |  | ABHISHEK SARAF |

Assignment 7

Problem Statement

- Prepare a software project plan with scheduling using Gantt charts and PERT charts for a sample project.

Gantt Chart

Gantt Summary Table

| Task | Start | End | Duration | Dependencies |
| --- | --- | --- | --- | --- |
| SoW Writing | W1 | W2 | 2 weeks | — |
| Architecture Design | W2 | W3 | 2 weeks | SoW |
| DFD / UML Diagrams | W3 | W4 | 2 weeks | Architecture |
| DB Schema Design | W3 | W4 | 1 week | Architecture |
| FastAPI Setup | W4 | W5 | 1 week | DB Schema |
| REST API + WebSocket | W5 | W6 | 2 weeks | FastAPI Setup |
| Data Prep & EDA | W4 | W5 | 1 week | DB Schema |
| Feature Engineering | W5 | W7 | 3 weeks | Data Prep |
| XGBoost Training | W6 | W7 | 2 weeks | Feature Eng. |
| Isolation Forest | W6 | W7 | 2 weeks | Feature Eng. |
| Ensemble + Threshold | W7 | W8 | 1 week | XGBoost + IF |
| Pre-Auth Engine | W5 | W7 | 2 weeks | REST API |
| Device Intelligence | W6 | W7 | 2 weeks | Pre-Auth |
| Graph Fraud Detector | W7 | W8 | 2 weeks | Pre-Auth |
| Phishing Protection | W7 | W8 | 2 weeks | Pre-Auth |
| Explainable AI | W8 | W9 | 2 weeks | All ML modules |
| Alert & Case Mgmt | W8 | W9 | 2 weeks | REST API |
| React/Vite Setup | W5 | W6 | 1 week | FastAPI |
| Dashboard UI | W6 | W8 | 3 weeks | React Setup |
| Charts & Simulation | W8 | W9 | 2 weeks | Dashboard UI |
| Integration Testing | W9 | W10 | 2 weeks | All above |
| Performance Tuning | W9 | W10 | 2 weeks | Integration |
| Bug Fixes | W10 | W11 | 1 week | Testing |
| README / SoW Final | W10 | W11 | 1 week | Testing |
| Pitch & Demo Prep | W11 | W12 | 2 weeks | All complete |

Pert Chart

PERT Formula

O = Optimistic time (best case)

M = Most Likely time

P = Pessimistic time (worst case)

Expected Time: tₑ = (O + 4M + P) / 6

Variance: σ² = ((P − O) / 6)²

Task Estimates

| Task ID | Task Name | O | M | P | te​ | σ2 |
| --- | --- | --- | --- | --- | --- | --- |
| T1 | SoW & Requirements | 1 | 2 | 3 | 2 | 0.11 |
| T2 | System Architecture | 1 | 2 | 4 | 2.2 | 0.25 |
| T3 | DFD + UML Diagrams | 1 | 1.5 | 3 | 1.7 | 0.11 |
| T4 | DB Schema | 0.5 | 1 | 2 | 1.1 | 0.06 |
| T5 | FastAPI Backend Setup | 0.5 | 1 | 2 | 1.1 | 0.06 |
| T6 | REST API + WebSocket | 1 | 2 | 4 | 2.2 | 0.25 |
| T7 | Data Prep & EDA | 1 | 1.5 | 3 | 1.7 | 0.11 |
| T8 | Feature Engineering | 2 | 3 | 5 | 3.2 | 0.25 |
| T9 | XGBoost Training | 1 | 2 | 4 | 2.2 | 0.25 |
| T10 | Isolation Forest | 0.5 | 1 | 2 | 1.1 | 0.06 |
| T11 | Ensemble Model | 0.5 | 1 | 2 | 1.1 | 0.06 |
| T12 | Pre-Auth Engine | 1 | 2 | 3 | 2 | 0.11 |
| T13 | Device Intelligence | 1 | 2 | 4 | 2.2 | 0.25 |
| T14 | Graph Fraud Detector | 1 | 2 | 4 | 2.2 | 0.25 |
| T15 | Phishing Protection | 1 | 1.5 | 3 | 1.7 | 0.11 |
| T16 | Explainable AI | 1 | 2 | 4 | 2.2 | 0.25 |
| T17 | Alert & Case Mgmt | 1 | 2 | 3 | 2 | 0.11 |
| T18 | React Dashboard | 1 | 2 | 4 | 2.2 | 0.25 |
| T19 | Charts & Simulation | 1 | 2 | 3 | 2 | 0.11 |
| T20 | Integration Testing | 1 | 2 | 4 | 2.2 | 0.25 |
| T21 | Performance Tuning | 0.5 | 1 | 2 | 1.1 | 0.06 |
| T22 | Documentation | 0.5 | 1 | 2 | 1.1 | 0.06 |
| T23 | Pitch & Demo Prep | 0.5 | 1 | 2 | 1.1 | 0.06 |

PERT Network Diagram

(START)

|

T1: SoW (2.0w)

|

T2: Architecture (2.2w)

|         \

T3:DFD    T4: DB Schema (1.1w)

(1.7w)    |           \

T5:FastAPI   T7:Data Prep

(1.1w)       (1.7w)

|             |

T6:API(2.2w)  T8:Feature Eng.(3.2w)

|             |       \

|          T9:XGB   T10:IF

|          (2.2w)   (1.1w)

|             \      /

|           T11:Ensemble(1.1w)

|                 |

T12:Pre-Auth(2.0w)   T16:XAI(2.2w)

/   \                     |

T13   T14                    |

T15   T17                    |

\     |    T18:React(2.2w)  |

\    |    T19:Charts(2.0w) |

\   |         |           |

T20: Integration Testing (2.2w)

|

T21: Perf Tuning (1.1w)

|

T22: Documentation (1.1w)

|

T23: Demo Prep (1.1w)

|

(END)

Critical Path Calculation

| Task | tₑ (weeks) | σ² |
| --- | --- | --- |
| T1: SoW | 2.0 | 0.11 |
| T2: Architecture | 2.2 | 0.25 |
| T4: DB Schema | 1.1 | 0.06 |
| T8: Feature Engineering | 3.2 | 0.25 |
| T9: XGBoost Training | 2.2 | 0.25 |
| T11: Ensemble | 1.1 | 0.06 |
| T12: Pre-Auth Engine | 2.0 | 0.11 |
| T16: Explainable AI | 2.2 | 0.25 |
| T20: Integration Testing | 2.2 | 0.25 |
| T21: Performance Tuning | 1.1 | 0.06 |
| T22: Documentation | 1.1 | 0.06 |
| T23: Demo Prep | 1.1 | 0.06 |
| TOTAL | 21.5 weeks | 1.77 |

Resultant PERT Chart

Milestones

| Milestone | Target Week | Description |
| --- | --- | --- |
| M1: Design Complete | End of W4 | SoW, architecture, DFDs, DB schema finalized |
| M2: Backend Live | End of W6 | FastAPI running with REST API and WebSocket |
| M3: ML Models Trained | End of W8 | XGBoost + ensemble + all advanced modules working |
| M4: Frontend Complete | End of W9 | Full React dashboard with live simulation |
| M5: System Integrated | End of W10 | Full end-to-end system verified |
| M6: Demo Ready | End of W12 | Pitch, demo video, documentation complete |